## Run of show
Event Run of Show
A minute-by-minute production schedule with cues, ownership, locations, and contingencies.
Event | Harbour Product Forum 2026
Date | 2026-09-17
Venue | Harbour Hall - Main Stage
Show caller | Maya Ortiz - radio channel 1
Start | End | Duration | Segment | Cue / action | Owner | Location | Status | Contingency
07:00 | 07:30 | 00:30 | Crew call | Safety briefing; radio and credential check. | Maya | Stage left | Confirmed | Late crew reports to production desk.
07:30 | 08:15 | 00:45 | Technical line check | Test lectern, playback, confidence monitor, and stream return. | Leo | Control room | Confirmed | Switch to backup playback laptop.
08:15 | 08:40 | 00:25 | Speaker rehearsal | Walk opening, panel handoff, and closing positions. | Nora | Main stage | Confirmed | Use marked standing positions only.
08:40 | 09:00 | 00:20 | Doors open | House music up; holding slide; ushers seat front rows last. | Imani | Auditorium | Confirmed | Delay doors by five minutes on caller cue.
09:00 | 09:05 | 00:05 | Show open | Lights to half; roll film A; host walks on at frame out. | Maya | Main stage | Ready | Host opens live if playback fails.
09:05 | 09:25 | 00:20 | Opening keynote | Slides K01-K18; two-minute warning at 09:23. | Avery | Main stage | Ready | Skip demo section if running over.
09:25 | 09:45 | 00:20 | Product demonstration | Roll camera 2 close-up; mirror device to screen. | Leo | Demo table | Ready | Use recorded demo B on device failure.
09:45 | 10:10 | 00:25 | Customer panel | Bring four chairs; handheld mics live; lower-third names. | Nora | Main stage | Ready | Drop audience Q&A if ten minutes late.
10:10 | 10:15 | 00:05 | Closing | Host recap; QR slide; thank sponsors; house lights full. | Maya | Main stage | Ready | Verbally read short URL if QR fails.
10:15 | 10:45 | 00:30 | Audience clear | Exit music; direct guests to foyer demos. | Imani | Auditorium | Ready | Open side exit if foyer queue backs up.
10:45 | 11:15 | 00:30 | Strike priority items | Power down demo devices; collect microphones and media drives. | Leo | Stage / control | Ready | Full scenic strike begins after venue sign-off.
Fictional event sample. The show caller controls live timing; venue safety instructions take priority.